## backlog
epic_id | epic_name | task_id | task_name | task_detail | type | status | owner | notes
0 | Data Setup | E0T1 | Download MIRACL-ID | Download corpus + train + dev splits dari HuggingFace MIRACL dataset | setup | done | Faiz | ~1.44M passages corpus + query splits
0 | Data Setup | E0T2 | Split train/val/test | 80/20 split dari MIRACL train set; seed=42; train=3257 val=814 test=960 queries | setup | done | Faiz | Test = MIRACL dev set (ada human qrels)
0 | Data Setup | E0T3 | Upload ke HuggingFace | Upload semua data ke fassabilf/umbrela-indo-ir dataset repo | setup | done | Faiz | Biar semua anggota tim bisa akses
1 | LLM Judge Inference | E1T1 | Qwen2.5-7B qrel generation | Generate qrels untuk semua split (test=9668 train=33076 val=8282 pairs) pakai prompt zeroshot_bing | experiment | done | Faiz | Bug fixed: filter None dari terminator tokens supaya kappa tidak NaN
1 | LLM Judge Inference | E1T2 | SahabatAI-Gemma2-9B qrel generation | Generate qrels untuk semua split; model Indonesian-specific | experiment | done | Radit | Pos rate 41.23% (lebih tinggi dari human 31.94%)
1 | LLM Judge Inference | E1T3 | SahabatAI-Llama3-8B qrel generation | Generate qrels; test selesai (9668); train baru 16829/33076 | experiment | done | Vincent | Default prompt pos rate 67% (kappa 0.21); butuh strict prompt untuk hasil wajar
1 | LLM Judge Inference | E1T4 | DeepSeek-V3 qrel generation | Generate qrels untuk test split (9668 pairs) via API | experiment | done | Vincent | Best judge: kappa=0.4219; paling konservatif (pos rate 27.99%)
1 | LLM Judge Inference | E1T5 | ChatGPT gpt-4o-mini qrel generation | Generate qrels via OpenAI API; partial 6751 pairs dari 9668 | experiment | done | Faiz | kappa=0.3856; API-based jadi paling mahal
2 | Kappa Analysis (RQ1) | E2T1 | Compute kappa per judge | Binarize LLM scores (score>=2 = relevant) lalu compute Cohen's kappa vs human qrels | analysis | done | Faiz | test: Qwen=0.3767 Gemma2=0.3763 Llama3=0.3652 DeepSeek=0.4219 GPT=0.3856
2 | Kappa Analysis (RQ1) | E2T2 | Compile kappa comparison table | Tabel semua judge + kappa + pos rate + n_pairs | analysis | done | Faiz | results/final/kappa*.csv
2 | Kappa Analysis (RQ1) | E2T3 | Analisis positivity rate per judge | Bandingkan pos rate LLM (28%-67%) vs human (31.94%); insight kalibrasi judge | analysis | done | Faiz | Range lebar: Llama3 default 66.66% vs DeepSeek 27.99%
3 | First-Stage Retrieval | E3T1 | BM25 top-100 all splits | BM25 pakai bm25s library (Java-free); k1=1.5 b=0.75; top-100 per query | experiment | done | Arvin | candidates/bm25_{train | val | test}_top100.jsonl
3 | First-Stage Retrieval | E3T2 | BGE-M3 dense retrieval top-100 | FAISS IndexFlatIP; multilingual embeddings; top-100 per query | experiment | done | Arvin | candidates/bgem3_{train | val | test}_top100.jsonl; nDCG@10=0.5604 (test)
3 | First-Stage Retrieval | E3T3 | Hybrid RRF fusion | Reciprocal Rank Fusion dari BM25 + BGE-M3 results | experiment | done | Arvin | nDCG@10=0.5191 (test)
3 | First-Stage Retrieval | E3T4 | Eval baseline semua retriever | Compute nDCG@10 MAP@10 Recall@100 untuk semua first-stage systems | analysis | done | Arvin | BM25=0.3053 BGE-M3=0.5604 Hybrid=0.5191
4 | Qwen Corpus Encoding | E4T1 | Encode 1.44M passages pakai Qwen | Qwen2.5-7B last-token pooling + L2 normalize; chunked batch untuk memory | experiment | done | Karol | ~20.8 GB total; 5 FAISS shards
4 | Qwen Corpus Encoding | E4T2 | Upload ke HuggingFace (5 shard) | Upload FAISS shards ke HF untuk akses tim; branch feat/e5-t2-qwen-corpus-encoding | setup | done | Karol | Query encode harus exact match: last-token pool + left-pad + L2 norm
4 | Qwen Corpus Encoding | E4T3 | Integrasi ke eval pipeline | Load 5 shard + concat + encode query dengan cara sama → generate candidates JSONL | setup | pending | Karol | Blocking untuk RQ3 (EPIC 6); Qwen-embed candidates belum ada
5 | Reranker Training + Eval (RQ2) | E5T1 | Triplet generation dari Qwen qrels | 53727 triplets dari 2866 queries; max 50 triplets/query; hard negatives dari Qwen-embed | setup | done | Faiz | reranker/prepare_data.py; hard neg = ranked tinggi tapi LLM label rel=0
5 | Reranker Training + Eval (RQ2) | E5T2 | Triplet generation dari Gemma2 qrels | Triplets dari Gemma2 qrels untuk size ablation | setup | done | Radit | Dipakai untuk N=100/300/500/1000/full experiments
5 | Reranker Training + Eval (RQ2) | E5T3 | Train BGE reranker on Qwen qrels | Fine-tune BAAI/bge-reranker-v2-m3; BCEWithLogitsLoss; AdamW lr=2e-5; 3 epochs RTX 4090 ~1.8h | experiment | done | Faiz | Loss: 0.49→0.27→0.10→0.029; model di fassabilf/umbrela-indo-ir-reranker-qwen
5 | Reranker Training + Eval (RQ2) | E5T4 | Size ablation reranker Gemma2 | Train 5 reranker dengan N=100/300/500/1000/full training queries; compare nDCG@10 | experiment | done | Radit | Best N=100 (1937 triplets) → nDCG@10=0.5178; overfitting ke LLM noise di N besar
5 | Reranker Training + Eval (RQ2) | E5T5 | Eval BM25 + Qwen reranker | Score BM25 top-100 pakai Qwen-trained reranker; eval vs human qrels | analysis | done | Faiz | nDCG@10=0.4478 MAP@10=0.3470 Recall@100=0.7634 (+46% vs BM25)
5 | Reranker Training + Eval (RQ2) | E5T6 | Eval BM25 + Gemma2 reranker per size | Eval semua 5 model dari size ablation | analysis | done | Radit | N=100→0.5178; N=300→0.4620; N=500→0.5011; N=1000→0.4072; full→0.3993
5 | Reranker Training + Eval (RQ2) | E5T7 | Plot learning curve | Plot nDCG@10 vs training size N dengan baseline overlays | analysis | done | Radit | results/final/learning_curve.png
5 | Reranker Training + Eval (RQ2) | E5T8 | Plot dual-axis ablation | Dual-axis plot: Val AP (LLM qrels) vs nDCG@10 (human qrels) per N | analysis | done | Radit | results/final/ap_vs_ndcg_curve.png; visualisasi overfitting ke LLM noise
5 | Reranker Training + Eval (RQ2) | E5T9 | Upload model ke HuggingFace | Upload fine-tuned reranker ke HF model repo | setup | done | Faiz | fassabilf/umbrela-indo-ir-reranker-qwen
6 | Bias Analysis (RQ3) | E6T1 | Rancang experiment matrix | Design matrix 2x2: (retriever: Qwen-embed vs BGE-M3) x (reranker: Qwen-rk vs Gemma2-rk) | analysis | pending | Karol | Goal: detect self-reinforcing bias dari judge/retriever choice
6 | Bias Analysis (RQ3) | E6T2 | Implement bias_analysis.py | Code evaluation matrix + delta nDCG@10 computation | analysis | pending | Karol | evaluation/bias_analysis.py sekarang masih TODO stub kosong; blocking
6 | Bias Analysis (RQ3) | E6T3 | Run eval matrix | Jalankan eval semua 4 kombinasi retriever x reranker | experiment | pending | Karol | Butuh E4T3 selesai dulu (Qwen-embed candidates)
6 | Bias Analysis (RQ3) | E6T4 | Analisis delta nDCG@10 | Apakah Qwen reranker perform lebih baik di atas Qwen-embed retrieval? Quantify bias. | analysis | pending | Karol | -
7 | Prompt Ablation | E7T1 | Eval zeroshot_bing vs zeroshot_basic | Run inference Qwen + Gemma2 dengan prompt zeroshot_basic; compute kappa; compare vs zeroshot_bing | experiment | pending | Radit | prompts/qrel_zeroshot_basic.txt vs qrel_zeroshot_bing.txt
7 | Prompt Ablation | E7T2 | Eval fewshot_bing vs fewshot_basic | Run inference dengan semua fewshot variants; compute kappa | experiment | pending | Radit | prompts/qrel_fewshot_bing.txt + qrel_fewshot_basic.txt; butuh GPU compute
7 | Prompt Ablation | E7T3 | Analisis strict prompt Llama3 | Investigasi kenapa default prompt Llama3 pos rate 67% sedangkan strict hanya 39% | analysis | pending | Vincent | Diff: format constraint di output? Model bias ke positive? \ | Karena kalau ga strict dia keluarin lebih dari 1 jawaban, dan tiap jawaban bisa beda beda.
7 | Prompt Ablation | E7T4 | Compile prompt ablation table | Tabel kappa per judge x prompt_mode | analysis | pending | - | Input untuk EPIC 8: pilih prompt terbaik sebelum LoRA
8 | LoRA Fine-tuning LLM Judge | E8T1 | Rancang LoRA setup | Pilih prompt terbaik dari EPIC 7; tentukan target layer LoRA; data split untuk fine-tuning | setup | pending | - | Depends on: E7T4 selesai; pakai human qrels sebagai training signal
8 | LoRA Fine-tuning LLM Judge | E8T2 | Fine-tune Qwen2.5-7B dengan LoRA | LoRA fine-tuning pada Qwen judge menggunakan human-labeled pairs; eval kappa | experiment | pending | - | Baseline: Qwen zeroshot kappa=0.3767
8 | LoRA Fine-tuning LLM Judge | E8T3 | Fine-tune SahabatAI dengan LoRA | LoRA fine-tuning pada Gemma2 atau Llama3 dengan setup sama | experiment | pending | - | Comparison: apakah Indonesian-specific model lebih improve dari LoRA?
8 | LoRA Fine-tuning LLM Judge | E8T4 | Eval kappa LoRA-tuned vs baseline | Bandingkan delta kappa dari LoRA: Qwen-LoRA vs SahabatAI-LoRA | analysis | pending | - | -
8 | LoRA Fine-tuning LLM Judge | E8T5 | Compare efficiency LoRA vs API judge | LoRA open-source (biaya GPU) vs DeepSeek-V3/GPT (biaya API); kappa per dollar | analysis | pending | - | DeepSeek-V3 kappa=0.4219; bisa LoRA open-source match ini?
9 | Paper / Laporan Akhir | E9T1 | Tulis section RQ1 | Narasi judge comparison; kappa table; analisis pos rate | analysis | pending | All | Depends: semua judge inference selesai (E1T3 masih in-progress)
9 | Paper / Laporan Akhir | E9T2 | Tulis section RQ2 | Narasi reranker training + size ablation insight (overfitting ke LLM noise) | analysis | pending | All | Hasil sudah ada semua; bisa dimulai
9 | Paper / Laporan Akhir | E9T3 | Tulis section RQ3 | Narasi bias analysis + interpretasi delta nDCG@10 | analysis | pending | Karol | Blocking: E6T4 harus selesai dulu
9 | Paper / Laporan Akhir | E9T4 | Compile final result tables | Satu tabel besar: semua judges x semua retriever x semua reranker | analysis | pending | All | -